## Table of Contents
Note: This document is a template any team can follow to establish a Grow Your Own Teacher Apprenticeship Program, and it should be used as a customizeable planning document. To be able to edit this document, be sure to download a copy.
Workbook: Grow Your Own Teacher Apprenticeship
|  | Contents | Description
Implementation Phases
Getting Started | 1 | Project Plan Tool | This table provides a project plan tool that outlines the steps needed to take a project from start to completion. It serves as a roadmap that shows the project phases, key milestones, key activities, owners, progress updates, and timeline.
Phase 1: Needs Assessment and Identifying Partners and Teams | 2 | Needs Assessment Tool | This tab provides a tool that can be utilized to collect and organize data to better understand the district staffing and employment needs.
Project Team Roles and Responsibilities
| 3 |  | This tab provides a template to outline the roles and responsibilities of those who will develop and operationalize a Grow Your Own Teacher Apprenticeship Program.
| 4 | Meeting Cadence | This tab provides a template to ensure teams have a meeting cadence that will set them up for success and create a space for consistent communication.
Phase 2: Designing an Apprenticeship | 5 | Budget Model | This tab provides a budget tool that can be utilized to determine the budget needed to start a Grow Your Own Teacher Apprenticeship Program and sustain fund it.
Phase 3: Launching Apprenticeship Program | 6 | Communications, Recruiting, and Marketing Planning Tool | This tab provides a planning tool that can be used to develop detailed communications, recruiting, and marketing plan.

## 1 - Project Plan
Project Plan | Description: This document's intended purpose is to provide an overview of the work that needs to be completed in order to successfully establish a Grow Your Own Teacher Apprenticeship Model. | Note: The project lead should be responsible for ensuring this document stays up to date. This document can be simplified or expanded based on how teams set up a program, but this template serves as a starting point.
Milestone | Activity | Owner/Required Stakeholders | Status/Percentage of Work Complete | MONTH |  |  |  | MONTH |  |  |  | MONTH |  |  |  | MONTH |  |  |  | MONTH
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Phase I: Developing Strong Partnerships (estimated time to complete: minimum of 3 months)
Task 1A: Complete a District Staffing Needs Assessment | Organize, collect, and review several years (recommended at least 3 years) of teacher human capital data
Interpret data and identify a key focus areas for the GYO Teacher Apprenticeship Program
Discuss the data and identify key focus areas for the GYO Teacher Apprenticeship Program based on the district's needs
Task 1B: Identify the Teaching Needs of the Local Community | Review EPP student enrollment and graduate data to identify potential representation gaps
Reach out to local schools to identify which teacher candidates are most in-need
Conduct outreach to local and partner districts to identify which specific grade-level and subject areas are of the greatest need
Hold a meeting to review data and determine which grade-level and subject areas the GYO program will focus on
Based on the needs identified in Task 1A and gaps identified in Task 1B, identiy specific focus areas for the program with the district and EPP partners present.
Task 1C: Identify a Strong District or EPP Partner | Collect useful information and data that can be utilized to identify partnership needs and fit
Reach out to possible partners and schedule meeting(s) to gain interest and capacity
Make a final decision on the best EPP / district partner
Task 1D: Identify a Source of Future Teachers | Brainstorm potential ideas for target recruitment populations
Engage with potential recruits to learn more about their interest and needs
Identify the source of teachers
Task 1E: Identify a Local Workforce Development Area Partner | Reach out to Local LWDA leadership
Request LWDA to join core project team and support the apprenticeship program
Task 1F: Identify Project Team Roles, Responsibilities, and a Meeting Cadence | Identify a project lead for the entire initiative, and leads from the district and EPP provider
Have leads from each key partner identify project team and share details with the project lead
Hold a meeting with the project lead + teams leads to finalize roles and responsibiltiies
Deliverable 1: Agree to an Initial Partnership Agreement | Draft a non-binding partnership agreement that includes key agreements from Tasks 1A-1F that partners agree to work towards as they develop an GYO Teacher Apprenticeship Proposal
Review the non-binding partnership agreement with each partnership's legal and leadership team
Adjust the agreement as necessary and obtain signatures from each partner project lead
Phase II: Teacher Apprenticeship Program Proposal (estimated time to complete: a minimum of 6 months)
Task 2A: Determine the Right Program Size | Identify the number of teachers the partnership will seek to train and in what specific grade and subject areas.
Task 2B: Design the Admissions Process | Confirm the number of apprentices that will be admitted into the program in each cohort for the next three years
Draft criteria for selecting apprentices to participate in the program
Draft the process for selecting apprentices for the program
Hold a feedback meeting with teams to get additional input on the criteria and admission process
Finalize criteria and the process for selecting apprentices
Task 2C: Design a Program of Structured On-The-Job Learning | Identify on-the-job learning learning structure and who will be responsible for facilitating it
Develop a plan that will outline how programs will ensure apprentices will gain proficiency in each on-the-job learning compentency over the three-year program
Task 2D: Design a Sequence of Related Instruction | Develop a plan that will outline the sequence of related instruction that will compliment the on-the-job learning
Develop the curriculum for the related instruction
Task 2E: Determine the Role of the Apprentice Teacher Aide | Determine the job description for the role
Task 2F: Identify Exit Requirements for Apprentices | Develop a criteria and process for confirming apprentices completed all the requirements for successful completion of the program
Task 2G: Ensure Comprehensive Support for All Apprentices | Identify a list of supports that your team can provide to apprentices
Develop a plan for how you will support your apprentices including financial support, monthly program development, etc.
Task 2H: Build an Adequate Budget and Staffing Model | Determine the staff needed for execution - mentor teachers, support staff, etc.
Develop job descriptions for all positions that need to be filled
Build out a budget that includes all aspects of the program (apprentice payments, comprehensive supports, tuition, mentor stipends, materials, teachers, etc).
Deliverable 2: Draft and Submit Program Proposal | Draft a program proposals that includes the identified design features from Tasks 2A-2H
Obtain sign-off from each project lead on the program proposal
Submit the draft program proposal to GrowYourOwn@tn.gov
Review the program proposal with TDOE and determine next steps based on TDOE feedback
Phase III: Launching an Apprenticeship Program (estimated time to complete: a minimum of 3 months)
Task 3.1 Establishing an MOU Between Partners | Draft MOUs for between the district, EPPs, and other partners
Finalize MOUs
Send out MOUs and get proper signatures
Task 3.2 Communications, Recruitment and Marketing Planning | Develop a communications and marketing plan
Develop a recruitment plan
Task 3.3 Defining Apprentice Expectations and Responsibilities | Finalize apprentice agreements and send them out to each participant
Task 3.4 Measuring Impact | Develop a plan for how data will be collected throughout the implementation of the program for correction, replication, refinement, etc.

## 2 - Needs Assessment Tool
Landscape Analysis Tool | Description: The first step in creating a GYO Teacher Apprenticeship Program is identifying the needs of the employing district. Assessing the teacher vacancies that currently exist will help identify target numbers for recruiting program participants to fill teacher vacancies, potential areas to train developing teachers, and specific areas of focus for the program. This template is intended to help teams gather and organize data to better support program design and implementation. | Note: These resources are meant to help guide thinking as teams start to identify the challenge area(s) they can address through GYO Teacher Apprenticeship Programs. This section coincides with pages 13-20 in the Playbook.
Identifying District Staffing Needs
Step 1: Collect and Organize Data
Areas of Focus | Targeted Data Collection Questions | Resources to Retrieve Data | Data
Demographics | What are the race/ethnicity, gender, age, experience, and languages spoken of current instructional staff?
Vacancies | How many teaching vacancies remain unfilled at the start of each year? How do these differ across grade/subject areas and schools?
Retention | How long have instructional staff been teaching with the district overall? How long at their current school? Do teachers generally have long tenures within the district or shorter? How does teacher retention differ across grades and subject areas? Across schools?
Retirement/Resignation/Non-Renewals | What trends are you seeing in retirements, resignations, and non-renewals over the last few years? How do these change across grade-levels and subject areas?
Certification Subject Area(s) | Which subject areas/grade levels are teachers endorsed in? Are there certain certification areas in need in which the district lacks a significant number of prepared teachers? What about permits or waivers?
Teacher Effectiveness Ratings | How do current teachers perform? Are teachers meeting performance standards? Are there challenging trends in any specific grade-levels or subject areas?
Step 2: Interpret Data and Identify Needs
Guiding Questions | Responses Based on Data | Notes
How does the teacher demographic profile compare to that of the students they teach? Where are there gaps?
Are teachers, with appropriate approvals, currently teaching outside of their certification area? Are there any schools/subject areas/grade levels where this is prevalent?
Are individuals currently teaching with provisional certification? Are there any schools/subject areas/grade levels where this is prevalent?
What is the experience level of the teaching workforce in terms of years of service? Are there any schools/subject areas/grade levels with more or less experienced teachers?
Are there any schools/subject areas/grade levels experiencing high turnover and vacancy rates?
Are there any schools/subject areas/grade levels where there is anticipated need for recruitment based on the trend in tenure level of current teachers?
How are Highly Effective (TVAAS Level 4 or 5) teachers distributed across schools/subject areas/grade levels? Are there areas where they are more concentrated compared to others? Are there Highly Effective teachers available to mentor apprentices in areas of program focus?
Identifying Employment Needs of Districts
Step 1: Collect and Organize Data
Areas of Focus | Data Collection Questions | Resources to Retrieve Data | Data
Meeting the Local Need of the Community | What are the demographics of program enrollment and graduates? What are the demographics of the state teacher workforce? What are the demographics of the state population? What are the demographics of the local community?
Meeting Positional Needs of Districts | What are the areas (specific grade-level and subject areas) of greatest need (i.e certified teachers, special education certified teachers, middle school)? How many students are enrolled in those areas? How many graduates are in those areas?
Step 2: Interpret Data and Identify Needs
Guiding Questions | Responses Based on Data | Notes
What is the data saying about the need of the local community? What is the data saying about student performance?
What is the data saying about the positional needs of the districts?

## 3 - Project Team Roles and Resp
Roles and Responsibilities | Description: Establishing the right project team and the correct division of roles and responsibilities between team members is critical for the long-term success of a Grow Your Own Teacher Apprenticeship Program. The following detail will support partnership launch and can serve as a template to support project preparedness. | Note: Districts and EPPs of certain sizes may have team representatives that represent several of these competencies. Understandably, team size and capacity will vary across district and EPP. For additional information, please review pages 23-25 of the Grow Your Own Teacher Apprenticeship Program Guidebook.
Overall Project Lead:
Who from each partner organization is on the project team, and how are the roles and responsibilities divided among team members?
Partner Role | Role and Responsibility | Contact Information (Name and Email)
Local Education Agency: This partner is responsible for supporting a pipeline of well-trained, well-supported teacher workforce. Responsibilities also include programming implementation within the district and schools. | Team Lead
Support Staff
Educator Preparation Program Provider: This partner is typically responsible for implementing the educator preparation programming, ensuring it is accessible, affordable, and in conjunction with the district supporting apprentice recruitment. | Team Lead:
Support Staff
Workforce Board Partner: This partner signs off on approval of registered apprentice program applications, offers support for potential additional funding, and guides apprenticeship development with expertise and input. | Team Lead:
Support Staff

## 4 - Meeting Cadence
Meeting Cadence | Description: Identifying the right meeting cadence is essential for ensuring key communication and progress can be made on the intended timeline for program launch. |  | Note: Teams should adjust their template and cadence accordingly given need, team size, deliverables, and shared timelines.
Meeting Cadence: How often will the project team and other stakeholders plan on meeting?
Group/Meeting Type | Meeting Frequency (weekly, monthly, quarterly) | Meeting Participants | Meeting Purpose/Objectives
LEA internal team meeting
EPP internal team meeting
Workforce Board internal team meeting
Full project team meeting (LEA + EPP + Workforce board teams)
Leadership Update Meetings
Other

## 5 - Budget Model
Budget Model | Description: This tool can be used to help determine the budget needed to successfully implement and sustain a Grow Your Own Teacher Apprenticeship Model. |  |  | Note: This template can be edited to align with program structure. This tool is simply to provide guidance as teams work through the budget. For more resources and guidance refer to pages 47-52 in the Playbook.
Develop a budget to outline how funds will be spent. This budget should represent a budget for all the years a the program will be in existence.
Program Staffing
Fiscal Year | Budget Item |  | Funding Source |  | Amount |  | Notes
Mentor Teachers
Educator Pipeline Facilitator
University Supervisor
TOTAL:
Related Instructional Costs
Tuition
Books and Materials
Assessment and Certification Costs
Additional instructional costs
TOTAL:
Calculating Apprentice Salaries
Apprentices should be paid a progressively increasing schedule of wages based on either a percentage or a dollar amount of the current hourly journey worker wage rate, which is: $27.42. Wage Progression (3-Year Term) Recommendation: Entry Level Wage: $14.48 1 st period: - $14.48 2 nd increase: – $14.63 3 rd increase: – $14.76 4 th increase: – $15.05 5 th increase: – $15.37 6 th increase: - $15.67 Completion of program and placement into a teacher position - $27.42
| Fiscal Year | Budget Item |  |  |  | Funding Source |  | # of teachers | Amount
Year 1
Year 2
Year 3
TOTAL:
Additional Apprentices Costs *if applicable
Fiscal Year | Budget Item |  | Funding Source |  | Amount
Average Salary
Social Security
Medicare
Retirement
Life Insurance

## 6 - Communications Plan Templat
Communications, Recruitment, and Marketing Plan | Description: This tab includes a template that can be utilized to help the team think through the starting, key components of a communications and engagement plan. The template can be adjusted to include more detail on specific deliverables, details, and local need. |  |  | Note: This template can be edited to align with program structure. For more resources and guidance refer to pages 55-57 in the Playbook.
Helpful Terms:
Stakeholder/Stakeholder Group: Define the audience that you will want to engage for the successful implementation of the program.
Purpose: Define the purpose for reaching out to the stakeholders/stakeholder groups for engagement.
Communication Tool: Outline the mechanisms and platforms to best engage the stakeholders outlined in this plan (i.e. newsletters, social media, in-person events, etc.).
Frequency: Determine how often will you be using the communication tools to engage stakeholders.
Owner: Identify the person who will be deploying the communication tools.
Stakeholder/Stakeholder Group | Purpose | Communication Tool | Frequency | Owner
Ex. High School Students (include specific schools that will be targeted) | Raise awareness about the program and recruit possible students who are interested in the the program. | -- In-person events (job fairs for high school students, have events at schools) | -- present at 3 job fairs --host two events at high schools
Timeline
Stakeholder | Activities | Timeframe
MONTH / YEAR
|  | Week 1 | Week 2 | Week 3
High School Student Engagement | Schedule job fairs
Prepare for job fairs
Schedule school visits
Prepare for school visits