## Slide 1: Wilson County
S.R. 109 Road Widening
From North of HWY 70 to South of Cumberland River
Project Length: 6.88 miles

## Slide 2: Existing Conditions
2 lane highway
Low level of service
  Average Daily Traffic: 23,880 vehicles (2018)
  During Peak Hour: 2,149 vehicles (9%)
  Projected Average Daily Traffic: 44,890 vehicles (2038)
  Truck traffic: 2149 vehicles (9%)

## Slide 3: Project Information
Part of the IMPROVE Act
Project let in December 2017
Lowest Bid: $50,924,616.81
Prime Contractor: Vulcan Materials Co.
Contract started: January 29th, 2018
Estimated completion date: November 30th, 2020

## Slide 4: Utilities Involved
Comcast
AT&T 
Sprint
ATMOS Energy
Middle TN Electric 
TVA
Charter
Laguardo Utility District 
West Wilson Utility District
City of Lebanon 
  Water and Sewer
  Gas
TransCanada (gas)
Level 3 Communications

## Slide 5: Road Widening
Road is increasing from 2 lanes to 5 lanes
  With 2 lanes in each direction, a 2 way turning lane, and shoulders

## Slide 6: North Terminus of Project
Walter T Durham Bridge
North Terminus

## Slide 7: South Terminus of Project
South Terminus
N
S
W
E

## Slide 8: Top Priority for Phase 1
Intersection at Academy Rd.
  Will be controlled by traffic signals
  2 intersection layouts
    Temporary
    Final
Academy Rd.

## Slide 9: Temporary Intersection
Existing SR109
Existing
Academy Road

## Slide 10: Final Intersection
Existing SR109
Existing
Academy Road

## Slide 11: Spencer Creek Bridge
Existing bridge: 85’ – 6” tee beams
  Proposed bridge: 140’ box beams

## Slide 12: Dry Fork Branch (Memorial Bridge)
Existing bridge: 85’ – 9” and tee beams
  Proposed bridge: 200’ and box beams

## Slide 13: Traffic Control During Construction
1 shift in traffic from S.R. 109 near Bloodworth Approximately 0.4 miles
A few road closures will occur throughout the life of the project
  Burton Road
  Bloodworth Road
  Northern Road
Speed limit will be reduced by 10 mph
Notes: Burton Road: US-70>Benders Ferry Road>Davis Corner Road
Northern Road (East portion of SR109): (NORTH) Double Log Cabin Road>Old Laguardo Road E (SOUTH) Old Laguardo Road E
Bloodworth Road: Creighton Lane>Woods Ferry Road
Northern Road closes during phase 2
opens upon completion
Burton closes during phase 1 and
opens in phase 2
Bloodworth closes during phase 1A
opens in phase 2

## Slide 14: Traffic Shift
Bloodworth
Road
Access Road
Access Road
State Route
109
Shift (0.4 miles)
N
S
W
E
* NOT TO SCALE

## Slide 15: Northern Road Closure
Old Laguardo
Road E
State Route
109
Northern
Road
N
S
W
E
Notes: CLOSES in phase 2 OPENS upon completion NO DETOUR ROUTES----- Take Old Laguardo Road

## Slide 16: Burton Road Closure
Burton Road
Davis Corner
Road
Benders
Ferry
Road
US-70
SR 109
N
S
W
E
Notes: CLOSES in phase 1 OPENS in phase 2 DETOUR ROUTE is shown: Approximately 10.5 mile detour to SR109

## Slide 17: Bloodworth Road Closure
State Route
109
Bloodworth
Road
Creighton Lane
Woods
Ferry Road
N
S
W
E
Notes: CLOSES in phase 1A OPENS in phase 2 NO DETOUR ROUTE STATED: Approximately 2 mile detour to SR109

## Slide 18: Lane Closure Restrictions
No traffic control restrictions from 5:30 a.m. to 9:30 a.m. and 3:30 p.m. to 6:00 p.m.
Holidays, Special Events, & Holiday Weekends
  All in accordance with specifications and Engineer

## Slide 19: New Safety Features Implemented
Smart Work Zone North
  4 portable message signs
  2 cameras
  5 portable radar detection devices
Smart Work Zone South
  7 portable message signs
  1 camera
  2 portable radar detection devices

## Slide 20: Contractor
Vulcan Materials Company
  Regional Construction Manager: Tim Murphy
  Project Manager: Mark Williams
  Grading Construction Manager: Kenny Black
  Project Superintendent: Luke Stinnet

## Slide 21: Construction Schedule
Preliminary Work (Feb. 2018 to Summer 2018)
Phase 1 (Feb. 2018 to Summer 2019)
  Traffic control
  Academy road intersection
  Construct temporary shift
Phase 2 (Summer 2019 to Nov. 2020)
  Traffic control
  Remove temporary shift
  Roadway and drainage work
  Spencer Creek Bridge
  Dry Fork Branch Bridge
  7 Box culverts
  Spencer Creek Bridge
  Dry Fork Branch Bridge
  Finish Box culverts

## Slide 22: Work With Us
We ask you to help keep us safe by practicing safe driving
Please be patient as we work to make S.R. 109 a more safe and efficient route

## Slide 23: TDOT Contacts
Project Supervisor
  Adam Vance, P.E.
    Phone: 615.898.8005
    Email: Adam.Vance@tn.gov
Community Relations Officer
  Kathryn Schulte
    Phone: 615.350.4302
    Email: Kathryn.Schulte@tn.gov
https://www.tn.gov/tdot/projects/region-3.html

## Slide 24: Questions?